## Stories
Sprint | Who | Story | Task | Estimate |  | Taken from http://www.agilenutshell.com/burndown
1 |  | 2017-09-22 | 2017-09-22
|  | US1 | T1 | 4
|  | US1 | T2 | 6
|  | US1 | T3 | 5
|  | US1 | T4 | 7
2 |  | 2017-09-29 | 2017-09-29 |  | 22
|  | US6 | T14 | 4
|  | US6 | T15 | 4
|  | US2 | T5 | 6
|  | US2 | T6 | 5
|  | US2 | T7 | 4
3 |  | 2017-10-06 | 2017-10-06 |  | 23
|  | US3 | T8 | 5
|  | US3 | T9 | 6
|  | US4 | T10 | 4
|  | US4 | T11 | 6
4 |  | 2017-10-13 | 2017-10-13 |  | 21
|  | US5 | T12 | 4
|  | US5 | T13 | 4
|  | US7 | T16 | 4
|  | US7 | T17 | 6
|  | US7 | T18 | 3
5 |  | 2017-10-20 | 2017-10-20 |  | 21
|  | US8 | T19 | 3
|  | US8 | T20 | 4
|  | US8 | T21 | 5
|  | US9 | T22 | 4
|  | US9 | T23 | 3
6 |  | 2017-10-27 | 2017-10-27 |  | 19
|  | US10 | T24 | 4
|  | US10 | T25 | 3
|  | US10 | T26 | 4
|  | US10 | T27 | 4
|  | US11 | T28 | 3
|  | US11 | T29 | 4
7 |  | 2017-11-03 | 2017-11-03 |  | 22
|  | US12 | T30 | 4
|  | US12 | T31 | 3
|  | US13 | T32 | 4
|  | US14 | T33 | 4
|  | US14 | T34 | 4
8 |  | 2017-11-10 | 2017-11-10 |  | 19
|  | US15 | T35 | 5
|  | US16 | T36 | 6
|  | US17 | T37 | 5
|  | US18 | T38 | 5
21
Release
|  |  | Total | 168
|  |  | Completed | 168
|  |  | Remaining | 0
|  |  | % Complete | 100%
|  |  | Avg Velocity | 21
|  |  | Estimated # Iterations Remaining | 0
Parking Lot
|  | Nice to have story #1 |  | 3
|  | Nice to have story #2 |  | 5
Dropped
|  | Stuff we didn't need #1 |  | 6
Stuff we didn't need #2
8 |  | #VALUE! | 1900-01-06 |  | 6
|  | US16 | T40 | 3
|  | US17 | T41 | 3
|  | US18 | T42 | 3

## Sprint Data
| 2017-09-22 | 2017-09-29 | 2017-10-06 | 2017-10-13 | 2017-10-20 | 2017-10-27 | 2017-11-03 | 2017-11-10
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8
Total Effort | 168 | 168 | 168 | 168 | 168 | 168 | 168 | 168
Velocity | 22 | 23 | 21 | 21 | 19 | 22 | 19 | 21
Remaining | 146 | 123 | 102 | 81 | 62 | 40 | 21 | 0
Completed | 22 | 45 | 66 | 87 | 106 | 128 | 147 | 168
% complete | 13.1% | 26.79% | 39.29% | 51.79% | 63.1% | 76.19% | 87.5% | 100%
Note on B3: es: This value needs to be updated to the cell which contains the total effort value if additional user stories are added to the list.
Note on B4: es: Velocity values need to be update if new user stories are added to the list to match the respective velocity/total work done cell for each sprint.