## Riders2Buyers
BURNDOWN CHART Riders 2 Buyers
Story ID # | User Story |  |  | Tasks | Task ID | Task Estimated Effort (Ideal Hours) | User Story Estimate (Ideal Hours) | Priority Ranking for User Stories
| As a | i want to | so that
1 | Customer | create an account | I can save my personal information
|  |  |  | Create sign up form | T1 | 4
|  |  |  | Implement database table for "Customer" | T2 | 6
|  |  |  | Create profile page | T3 | 5
|  |  |  | Write authetication script | T4 | 7
[7 empty] | 22 | 1
2 | Customer | Browse different car available | I can get car on rental or purchase car
|  |  |  | Implementing database for "cars" | T5 | 6
|  |  |  | Create page displaying car available on rent/purchase | T6 | 5
|  |  |  | Create webpage to display individual car details | T7 | 4
[7 empty] | 15 | 3
3 | Customer | Enter Journey details | I can obtain quotes from that details
|  |  |  | Create form for taking journey details | T8 | 5
|  |  |  | Create page displaying car details and rental cost | T9 | 6
[7 empty] | 11 | 4
4 | Customer | Enter desired car details | I can purchase a car
|  |  |  | Create form for taking customer requirements | T10 | 4
|  |  |  | Create page displaying car details and cost | T11 | 6
[7 empty] | 10 | 5
5 | Customer | filter from availability of different cars | I can narrow down search result
|  |  |  | Implement the functionality for filter option and filter parameters | T12 | 4
|  |  |  | Create a page displaying filtres applied and search result as per filter. | T13 | 4
[7 empty] | 8 | 6
6 | Customer | login to app | I can find details for rent/purchase a car
|  |  |  | Create a page for the user to Login | T14 | 4
|  |  |  | Implement user authentication functionality | T15 | 4
[7 empty] | 8 | 2
7 | Customer | Make payment | I can get car on rent or to purchase
|  |  |  | Create payment page | T16 | 4
|  |  |  | Implement Third party payment Integration | T17 | 6
|  |  |  | Generate reciept | T18 | 3
[7 empty] | 13 | 7
8 | Customer | Get reciept details | I can view payment details | Create payment database | T19 | 3
|  |  |  | Implement payment database | T20 | 4
|  |  |  | Create rides history page | T21 | 5
[7 empty] | 12 | 8
9 | Customer | write review/ to rate | Review can help users
|  |  |  | Implement "Reviews" database | T22 | 4
|  |  |  | Create review and rating system page | T23 | 3
[7 empty] | 7 | 9
10 | Seller | create an account | I can save my personal information
|  |  |  | Create a Seller registration page | T24 | 4
|  |  |  | Create database table for Seller | T25 | 3
|  |  |  | Implement database table for Seller | T26 | 4
|  |  |  | Create profile page | T27 | 4 | 15 | 10
11 | Seller | Provide car details | Customers will have the details
|  |  |  | Create form to take car details | T28 | 3
|  |  |  | Store the data in cars database | T29 | 4 | 7
11
12 | Seller | get reciepts for transactions | I can view previous payment details
|  |  |  | Implement Sellers transactions retrieval | T30 | 4
|  |  |  | Create transactions history page for seller | T31 | 3 | 7 | 12
13 | Seller | check reviews car | I can make necessary improvements in car | To create review and rating page for seller | T32 | 4 | 4 | 13
14 | Employee of Refurbishment Department | Provide refurbishment quotation to user | user can get refurbishment quotes
|  |  |  | create a page for taking user requirements. | T33 | 4
|  |  |  | Create page to display cost of each component and total billing. | T34 | 4 | 8 | 14
15 | Employee of Refurbishment Department | Examine car after rental ride | car's quality is assured
|  |  |  | Create page to display cost of each component and total billing incase of accident to customer. | T35 | 5 | 5 | 15
16 | Accounts Department Employee | give quotation to user | user can view details | Create quotation page | T36 | 6 | 6 | 16
17 | Accounts Department Employee | Provide seller with bills | seller can view his previous bills. | Create bill page for sellers | T37 | 5 | 5 | 17
18 | Accounts Department Employee | Provide customer with bills | customer can view his previous bills. | Create bill page for customers | T38 | 5 | 5 | 18